## Sheet1
System Name: Recipe Sharing Community System
Members: Antonio Kho, Raymund Laude, John Kenneth Baguio
Statuses |  | Todo
In-Progress
Done
On-hold
[5 empty] | August |  |  |  | September |  |  |  | October |  |  |  | November
Tasks | Assignee | Date Started | Date Finished | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1. Introduction | Kho,Laude | 21/08/2024 | 31/08/2024 | Done
1.1 Document Purpose | Kho,Laude | 21/08/2024 | 31/08/2024 | Done
1.2 Document Scope | Kho,Laude | 21/08/2024 | 31/08/2024 | Done
1.3 Document Audience | Kho,Laude | 31/08/2024 | 31/08/2024 | Done
1.4 Business Analysis Approach | Kho,Laude | 31/08/2024 | 31/08/2024 | Done
2. System Architecture & Functional Overview | Kho,Laude | 31/08/2024 | 31/08/2024 | Done
2.1 Platform Overview and System Components | Kho,Laude | 31/08/2024 | 31/08/2024 | Done
2.2 Functions Requirements | Kho,Laude | 31/08/2024 | 31/08/2024 | Done
2.3 Logical Data Model | Kho,Laude | 31/08/2024 | 31/08/2024 | Done
Creation of repository | Kho,Laude,Baguio | 23/09/2024 |  | In-progress
Creation of ERD and UI/UX | Kho,Laude,Baguio | 23/09/2024 |  | In-progress